## T-Pilot
Summary | Issue key | Description | Priority | Status | Linked Issues
Valid users sometimes can’t log in | UEO-100 | Correct credentials get “Invalid username or password.” Intermittent, affects ~5% of login attempts. | Critical | To Do | UEO-106
Search returns zero results for popular queries | UEO-101 | Queries like “wireless mouse” show “No items found,” despite index containing matching SKUs. | High | In Progress | UEO-106, UEO-111
Cart update fails when quantity >1 | UEO-102 | Adding a quantity >1 triggers “500 Internal Server Error” on POST /cart/update | Major | To Do | UEO-107
Checkout payment times out | UEO-103 | After clicking “Pay,” the spinner never stops; eventually a gateway timeout error appears. | Critical | To Do | UEO-102, UEO-108
Forgot-password email never arrives | UEO-104 | Users receive no email after submitting “Forgot Password.” SMTP logs show “queued” but never sent. | High | Done | UEO-109
Profile-picture upload rejects valid JPEGs | UEO-105 | Uploading a JPEG returns “Unsupported format.” PNG and GIF still accepted. | Minor | In Progress | UEO-110
Product-indexer service down occasionally | UEO-106 | GET /search/index returns 503 sometimes, causing downstream search failures. | Critical | To Do | —
Quantity-validation library throws schema errors | UEO-107 | New quantity-validator NPM package v2.1.0 throws “Schema mismatch” when quantity >1. | Major | In Progress | —
Payment gateway returns HTTP 502 | UEO-108 | Third-party gateway returns 502 Bad Gateway intermittently (~1 in 100 payments). | Critical | To Do | —
Email service rejects reset requests when queue full | UEO-109 | Under high load, SMTP queue rejects new messages with “421 Too many connections.” | High | Done | —
File-validator misclassifies valid JPEGs as BMP | UEO-110 | The file-validator utility labels true JPEGs as BMP, causing the upload rejection. | Minor | In Progress | —
Multilingual search fails for accented characters | UEO-111 | Queries with accents (“café grinder”) return no hits, though plain “cafe” works. | Low | To Do | UEO-101, UEO-106
Discount codes not applied at checkout | UEO-112 | Entering valid code “SUMMER21” leaves total unchanged; no error message displayed. | Major | To Do | UEO-102, UEO-103
Order history page blank for recent orders | UEO-113 | Navigating to “My Orders” after checkout shows empty table even though orders exist in DB. | High | To Do | UEO-103